Here’s your complete SevaSetu India Project Plan (with all major tasks grouped + priority levels + dependencies).
It’s designed so we can execute in parallel — one track technical, one track operational/business.

# 📘 SevaSetu India – Complete Project Plan

(U&M Execution & Documentation Roadmap)
Phase: Foundation + Expansion | Duration: Nov 2025 – Feb 2026

## 🧩 PHASE 1 – FINALIZE CORE SYSTEM (Ready for Public & Partner Use)

Goal: Make the current app fully functional, bug-free, and deploy-ready with docs.

| # | Task | Description | Priority | Status |
| --- | --- | --- | --- | --- |
| 1 | ✅ Navbar/Menu Complete | All pages linked & responsive (Home, Services, About, Contact, Admin) | 🔥 High | ✅ Done |
| 2 | ✅ Footer Setup | Add Terms, Privacy, Partner links, App Store icons | 🔥 High | ⚙️ Partial |
| 3 | 🧭 Terms & Privacy Pages | Create content + link in footer | 🔥 High | ⏳ Pending |
| 4 | 🧭 Partner / Join Page | Professional onboarding info + CTA | 🔥 High | ⏳ Pending |
| 5 | 📍 Contact Integration | Firestore + Cloud Function + Email setup | 🔥 High | ✅ Done |
| 6 | 🧭 About Page | Final visuals + team intro | Medium | ✅ Done |
| 7 | ⚙️ Admin Support Dashboard | Working ticket system & analytics | 🔥 High | ✅ Done |
| 8 | 🧱 Mobile Optimization | Fix Navbar delay, optimize load speed | 🔥 High | ⏳ Pending |
| 9 | ⚙️ Performance Tuning | Lighthouse speed test >90 on mobile | Medium | ⏳ Pending |
| 10 | 🧾 Firebase Hosting + Vercel Sync | Keep both active for redundancy | Medium | ✅ Done |

## 📊 PHASE 2 – REAL DATA & ONBOARDING (Operational Launch)

Goal: Start collecting actual provider data, setting up real-world SevaSetu ops.

| # | Task | Description | Priority | Owner | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | 📄 Provider Onboarding Template | Standard Excel/Firestore structure | 🔥 High | Me | ⏳ Planned |
| 2 | 📊 Financial Model Sheet | Earnings, margins, U&M benefit | 🔥 High | Both | ⏳ Planned |
| 3 | 🧾 Provider Verification Flow | Aadhaar, docs, photo, police check | Medium | You | ⏳ Planned |
| 4 | 💰 Payment Flow | Decide payout % + integration (Razorpay) | 🔥 High | Me | ⏳ Planned |
| 5 | 📋 Provider App/Web Form | Firebase-based intake (manual + self) | Medium | Me | ⏳ Planned |
| 6 | 🧾 Contract Templates | Provider Agreement + NDA | Medium | You | ⏳ Planned |
| 7 | 📞 Partnership Campaign | Start local onboarding (Ghaziabad) | 🔥 High | You | ⏳ Planned |

## 🧠 PHASE 3 – BUSINESS DOCUMENTATION (System Bible & Reports)

Goal: Make SevaSetu a replicable, documented model.

| # | Task | Description | Priority | Output | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | 📘 SevaSetu System Bible | Master technical doc (UI, DB, APIs, Flow) | 🔥 High | Word/PDF | ⚙️ Starting |
| 2 | 🧾 Deployment Logs | Daily logs of updates + outputs | Medium | Word | ⚙️ Active |
| 3 | 🧮 Provider Economics Doc | Earnings comparison & ROI | 🔥 High | Excel/Word | ⏳ Planned |
| 4 | 📑 Field Manual | “How to onboard providers” (Hindi-English mix) | Medium | PDF | ⏳ Planned |
| 5 | 📊 Dashboard Report Design | Monthly report template (service stats) | Medium | PowerPoint | ⏳ Planned |
| 6 | 📂 Database Schema Diagram | Firestore collections visualization | Medium | PNG/PDF | ⏳ Planned |
| 7 | 📋 Version Control Log | Track changes & deployment builds | Medium | Markdown | ⏳ Planned |

## 🚀 PHASE 4 – GROWTH & AUTOMATION (Expansion)

Goal: Scale operations, automate reports, and expand services.

| # | Task | Description | Priority | Status |
| --- | --- | --- | --- | --- |
| 1 | 📈 Booking System 2.0 | Add calendar + multi-booking option | Medium | ⏳ Future |
| 2 | 📞 Customer Support Chat | Add in-app chat (Firebase Realtime DB) | Medium | ⏳ Future |
| 3 | 🔄 Payment Automation | Razorpay payout + receipt system | High | ⏳ Future |
| 4 | 📅 Analytics Dashboard | Auto summary of monthly revenue | High | ⏳ Future |
| 5 | 🌐 Local Ads / Offers | Service-level promotions & upsells | Medium | ⏳ Future |
| 6 | 🧾 Multilingual UI | Hindi / English switch | Medium | ⏳ Future |
| 7 | 🧍‍♂️ Professional Portal | Provider login + earnings view | 🔥 High | ⏳ Future |

## 🕐 Execution Approach

We’ll work in Parallel Sprint Model:

| Track | Owner | Type | Duration | Output |
| --- | --- | --- | --- | --- |
| 🧱 Core System & UI Fixes | Me | Technical | Daily | Deployed Build |
| 💰 Provider + Business Model | You | Business | Daily | Sheets + Docs |
| 📘 System Bible | Me | Documentation | Ongoing | Word Doc |
| 📞 Partnership Onboarding | You | Field Ops | Weekly | Real Providers |

## 🧾 Deliverables (Daily/Weekly Output)

| Frequency | Deliverable | Format |
| --- | --- | --- |
| Daily | Progress Summary + Change Log | Chat / Doc |
| 2–3 days | Deployment / Backup Report | Word |
| Weekly | Updated System Bible | PDF |
| Weekly | Business Sheet (Financials + Leads) | Excel |
| Monthly | Expansion Report (Leads + Cities) | PPT |

## 🧩 NEXT ACTION (Tomorrow Plan)

Morning Session:

- ✅ Prepare “System Bible Cover + TOC Layout” (Word doc)

- ✅ Review current mobile UI bug (Navbar & service cards)

- ✅ Create Provider Onboarding Excel (with Firestore mapping)

- ✅ Begin Financial Model Sheet (provider vs platform)

Evening Session:

- 🔹 Deploy small UI fixes (mobile optimization)

- 🔹 Finalize and commit Bible layout & Excel template

- 🔹 Update GitHub and deploy new build

Would you like me to:

- 🧾 Generate this entire Project Plan into a professional .docx (with logo, table layout, headers & categories)
so you can keep it as SevaSetu Master Plan – Phase 2 (Nov 2025)
and we’ll start marking progress line by line tomorrow?

++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++

## 🧭 SevaSetu Master Project Task List (Full Scope)

### 🟦 1️⃣ Customer Module

| # | Task | Status | ETA | Priority |
| --- | --- | --- | --- | --- |
| C1 | Booking Flow UI + UX Finalization | ⏳ In Progress | Nov 2 | 🔴 High |
| C2 | Add Thank You Page (with ✅ animation) | ✅ Done | — | 🟢 |
| C3 | Feedback Widget Integration (show + submit) | ✅ Done | — | 🟢 |
| C4 | Feedback Database Connection (Firestore) | ✅ Done | — | 🟢 |
| C5 | Booking Confirmation Redirect to Feedback | ⏳ Pending | Nov 2 | 🔴 High |
| C6 | OTP Verification for Booking Users | ✅ Done | — | 🟢 |
| C7 | Mobile Responsive Layout Fixes | ⏳ In Progress | Nov 3 | 🟠 Medium |
| C8 | Customer Dashboard Summary (My Bookings) | ⏳ Planned | Nov 5 | 🟡 Medium |
| C9 | Service Rating + Edit Feedback | 🕓 Planned | Nov 6 | 🟡 |
| C10 | Push Notification Integration | ⏳ Future | Nov 10 | ⚪ Low |

### 🟧 2️⃣ Service Provider Module

| # | Task | Status | ETA | Priority |
| --- | --- | --- | --- | --- |
| S1 | Provider Registration Form + OTP | ⏳ In Progress | Nov 3 | 🔴 |
| S2 | Provider Dashboard (Earnings + Bookings) | 🕓 Planned | Nov 4 | 🟡 |
| S3 | Service Category Selection UI | ✅ Done | — | 🟢 |
| S4 | Availability Toggle (Online/Offline) | 🕓 Planned | Nov 5 | 🟠 |
| S5 | Add/View Feedback by Customers | ⏳ Pending | Nov 5 | 🟡 |
| S6 | Provider Profile Edit & Upload (Photo, Docs) | 🕓 Planned | Nov 6 | 🟡 |
| S7 | Earnings Summary Graph | 🕓 Planned | Nov 7 | 🟡 |
| S8 | Logout + Account Delete Flow | ✅ Done | — | 🟢 |

### 🟨 3️⃣ Admin / Operations

| # | Task | Status | ETA | Priority |
| --- | --- | --- | --- | --- |
| A1 | Admin Login & Role Guard | ✅ Done | — | 🟢 |
| A2 | Dashboard Overview (Bookings, Feedback) | ✅ Done | — | 🟢 |
| A3 | Reports UI – Bookings Summary Table | ⏳ In Progress | Nov 2 | 🟠 |
| A4 | Feedback Review Page | 🕓 Planned | Nov 3 | 🟡 |
| A5 | Bug Tracker Integration (auto import sheet) | ⏳ Pending | Nov 4 | 🟠 |
| A6 | Add User Management Tab | 🕓 Planned | Nov 5 | 🟡 |
| A7 | Analytics Graph (Bookings Trend, Feedback Rating) | 🕓 Planned | Nov 6 | 🟡 |
| A8 | Admin Notification Control (Email/Push) | 🕓 Future | Nov 9 | ⚪ Low |
| A9 | Firestore Role Update APIs | ✅ Done | — | 🟢 |

### 🟩 4️⃣ Costing & Payments

| # | Task | Status | ETA | Priority |
| --- | --- | --- | --- | --- |
| P1 | Costing Table Schema (Firestore) | ✅ Done | — | 🟢 |
| P2 | Admin Service Cost Override | ⏳ Pending | Nov 4 | 🔴 |
| P3 | Dynamic GST + Platform Fee Calculation | ⏳ Pending | Nov 4 | 🔴 |
| P4 | Payment Gateway (Stripe / Razorpay) | 🕓 Future | Nov 7 | 🟡 |
| P5 | Auto Email Receipt after Payment | 🕓 Planned | Nov 8 | 🟡 |
| P6 | Refund / Cancellation Logic | 🕓 Future | Nov 10 | ⚪ Low |

### 🟪 5️⃣ Reports & Analytics

| # | Task | Status | ETA | Priority |
| --- | --- | --- | --- | --- |
| R1 | Feedback Summary Report | ⏳ Pending | Nov 5 | 🟠 |
| R2 | Waitlist User Growth Report | ⏳ Pending | Nov 5 | 🟠 |
| R3 | Booking Revenue Chart (Month-wise) | 🕓 Planned | Nov 6 | 🟡 |
| R4 | Export to CSV/PDF | 🕓 Planned | Nov 6 | 🟡 |
| R5 | Dashboard Graph for Daily Bookings | 🕓 Planned | Nov 6 | 🟡 |
| R6 | Service Category Trend Analysis | 🕓 Planned | Nov 8 | 🟡 |

### 🟫 6️⃣ Backend / Infrastructure

| # | Task | Status | ETA | Priority |
| --- | --- | --- | --- | --- |
| B1 | Firebase Hosting (Production + Dev) | ✅ Done | — | 🟢 |
| B2 | Firestore Rules + Optimization | ✅ Done | — | 🟢 |
| B3 | Firebase Auth Domain Whitelist | ✅ Done | — | 🟢 |
| B4 | Automatic Daily Backup (Cloud Function) | ✅ Done | — | 🟢 |
| B5 | CI/CD with GitHub Actions + Vercel | ⏳ Pending | Nov 1 | 🟠 |
| B6 | Error Logging via Firebase Functions | 🕓 Planned | Nov 4 | 🟡 |
| B7 | Analytics Event Tracking | 🕓 Planned | Nov 6 | 🟡 |
| B8 | Firebase Region Failover Setup | 🕓 Future | Nov 10 | ⚪ Low |

### 🟥 7️⃣ Bug / Issue Tracker

| # | Task | Status | ETA | Priority |
| --- | --- | --- | --- | --- |
| BG1 | Create Tracker Sheet (auto) | ✅ Done | — | 🟢 |
| BG2 | Add Conditional Color Logic | ⏳ Pending | Nov 1 | 🟠 |
| BG3 | Auto ID Generator (B001...) | ✅ Done | — | 🟢 |
| BG4 | Link Admin “Bugs” Tab to Sheet | 🕓 Planned | Nov 3 | 🟡 |
| BG5 | Add Auto “Last Updated” Cell | ⏳ Pending | Nov 1 | 🟠 |
| BG6 | Daily Report Export to PDF | 🕓 Planned | Nov 6 | 🟡 |

### 📊 8️⃣ Reports Summary (Dashboard Tracker Sync)

| Key Metric | Current | Target | Status |
| --- | --- | --- | --- |
| Customer Features | 80% | 100% | 🟡 Medium |
| Provider Features | 60% | 100% | 🟠 In Progress |
| Admin Features | 70% | 100% | 🟡 Medium |
| Costing | 40% | 100% | 🔴 |
| Backend | 85% | 100% | 🟢 Stable |
| Reports/Analytics | 50% | 100% | 🟡 |
| Bugs Fixed | 2 | 20 | 🟡 |
| Overall Project Progress | 67% | 100% | 🟢 On Track |

Would you like me to:

- 🧾 Auto-convert this list into the Excel tracker (v1.3) with columns for owner, ETA, and conditional color formatting —
OR

- 📋 Just export this as a Markdown/CSV file first for manual review before importing into Excel?

👉 Which do you prefer (option 1 or 2)?