## Dashboard Summary
Module | Total Tasks | Completed | Pending | % Complete | Status | Next Milestone
Customer | 10 | 4 | 6 | =IF(B2=0 | 0 | ROUND(C2/B2*100 | 0)) | In Progress | Booking Flow UI (Nov 2)
Service Provider | 8 | 3 | 5 | =IF(B3=0 | 0 | ROUND(C3/B3*100 | 0)) | In Progress | Registration (Nov 3)
Admin / Ops | 9 | 5 | 4 | =IF(B4=0 | 0 | ROUND(C4/B4*100 | 0)) | Good | Reports UI (Nov 2)
Costing | 6 | 1 | 5 | =IF(B5=0 | 0 | ROUND(C5/B5*100 | 0)) | Low Progress | Pricing Logic (Nov 4)
Reports & Analytics | 6 | 1 | 5 | =IF(B6=0 | 0 | ROUND(C6/B6*100 | 0)) | Low Progress | Analytics (Nov 5)
Backend / Infra | 8 | 5 | 3 | =IF(B7=0 | 0 | ROUND(C7/B7*100 | 0)) | Stable | Vercel Integration (Nov 1)
TOTAL | 47 | 19 | 28 | =IF(B8=0 | 0 | ROUND(C8/B8*100 | 0))

## Detailed Tracker
ID,Module,Task,Description,Owner,Start Date,Target Date,% Complete,Status,Notes
C1,Customer,Home Page,Service Discovery UI,Akhsey,2025-10-28,2025-10-29,100,Done,Verified
C3,Customer,Booking Flow,Select + Schedule Service,Akhsey,2025-11-02,2025-11-03,0,Planned,Design Pending
SP1,Provider,Registration / KYC,Provider Sign-Up + Docs,Akhsey,2025-11-03,2025-11-04,0,Planned,
A4,Admin / Ops,Dashboard Reports,Graphs + Data for Admin,Akhsey,2025-11-04,2025-11-05,50,Partial,Firestore Linkage
COST1,Costing,Dynamic Pricing,Variable Pricing Per City,Akhsey,2025-11-05,2025-11-06,0,Planned,
R2,Reports & Analytics,Provider Ratings,Ratings Summary Per Provider,Akhsey,2025-11-06,2025-11-07,0,Planned,

## Milestones
Milestone,Description,Target Date,Status,Dependencies
MVP Alpha Launch,OTP + Waitlist Live,2025-10-30,Done,Firebase Auth
Feedback Flow,Rating + Thank You Page,2025-10-31,Done,Feedback DB
reCAPTCHA Invisible,Hide Visible Widget,2025-10-31,In Progress,LaunchingSoonWidget
GitHub + Vercel Sync,Connect Repos & CI,2025-10-31,In Progress,GitHub

## Change Log
Date,Change,Description,By,Status
2025-10-30,Firebase Hosting,Production Deployed,Akhsey,Done
2025-10-31,Feedback UI,Thank-You Animation Added,Akhsey,Done
2025-10-31,OTP Widget,Production Success,Akhsey,Done
2025-11-01,Tracker Setup,Master Tracker Created,Akhsey,Planned

## Next SprintPriority,Task,Owner,
Priority,Task,Owner,Planned Date,Status
High,reCAPTCHA Invisible Fix,Akhsey,2025-11-01,Planned
High,GitHub & Vercel Sync,Akhsey,2025-11-01,Planned
Medium,Booking Flow UI,Akhsey,2025-11-02,Planned
Medium,Provider Registration,Akhsey,2025-11-03,Planned
Medium,Costing Model Integration,Akhsey,2025-11-04,Planned

## Auto Summary
Metric,Value
Total Tasks,=SUM('Dashboard Summary'!B2:B7)
Completed,=SUM('Dashboard Summary'!C2:C7)
Overall %,=IF(B1=0,0,ROUND(B2/B1*100,0))
Active Modules,=COUNTA('Dashboard Summary'!A2:A7)
Next Milestone,=INDEX('Dashboard Summary'!G2:G7,MATCH(MIN('Dashboard Summary'!C2:C7),'Dashboard Summary'!C2:C7,0))

## Bug_Issue Tracker
ID,Module,Reported By,Date Reported,Severity,Issue Title,Description,Status,Owner,Target Fix Date,Date Resolved,Resolution Notes,Days Open,Overdue
B001,Customer,Akhsey,2025-10-31,High,OTP Verification Loop,"OTP not verifying properly in dev environment","Resolved",Dev Team,2025-10-31,2025-10-31,"ReCaptcha reinit fixed",=IF(K2="",TODAY()-D2,K2-D2),=IF(AND(K2="",J2<TODAY()),"⚠️ Yes","No")
B002,Feedback,Akhsey,2025-10-31,Medium,Feedback Form Alignment,"Fields not aligned after animation update","Resolved",UI Team,2025-10-31,2025-10-31,"CSS grid adjusted",=IF(K3="",TODAY()-D3,K3-D3),=IF(AND(K3="",J3<TODAY()),"⚠️ Yes","No")
B003,Admin,Akhsey,2025-11-01,Low,Report Table Pagination,"Admin table shows only 10 rows","Open",Dev Team,2025-11-02,,"Pending pagination logic",=IF(K4="",TODAY()-D4,K4-D4),=IF(AND(K4="",J4<TODAY()),"⚠️ Yes","No")
B004,Provider,Akhsey,2025-11-01,High,Provider Registration Crash,"Error on submit after KYC upload","In Progress",Backend,2025-11-02,,"Investigating storage limits",=IF(K5="",TODAY()-D5,K5-D5),=IF(AND(K5="",J5<TODAY()),"⚠️ Yes","No")