## Dashboard Summary
Module | Total Tasks | Completed | Pending | % Complete | Status | Next Milestone
Customer | 10 | 4 | 6 | =IF(B2=0 | 0 | ROUND(C2/B2*100 | 0)) | In Progress | Booking Flow UI (Nov 2)
Service Provider | 8 | 3 | 5 | =IF(B3=0 | 0 | ROUND(C3/B3*100 | 0)) | In Progress | Registration (Nov 3)
Admin / Ops | 9 | 5 | 4 | =IF(B4=0 | 0 | ROUND(C4/B4*100 | 0)) | Good | Reports UI (Nov 2)
Costing | 6 | 1 | 5 | =IF(B5=0 | 0 | ROUND(C5/B5*100 | 0)) | Low Progress | Pricing Logic (Nov 4)
Reports & Analytics | 6 | 1 | 5 | =IF(B6=0 | 0 | ROUND(C6/B6*100 | 0)) | Low Progress | Analytics (Nov 5)
Backend / Infra | 8 | 5 | 3 | =IF(B7=0 | 0 | ROUND(C7/B7*100 | 0)) | Stable | Vercel Integration (Nov 1)
TOTAL | 47 | 19 | 28 | =IF(B8=0 | 0 | ROUND(C8/B8*100 | 0))
Bug_Issue_Tracker | 3 | 2 | 1 | 67 | Monitoring | Daily Review

## Detailed Tracker
ID | Module | Task | Description | Owner | Start Date | Target Date | % Complete | Status | Notes
C1 | Customer | Home Page | Service Discovery UI | Akhsey | 2025-10-28 | 2025-10-29 | 100 | Done | Verified
C3 | Customer | Booking Flow | Select + Schedule Service | Akhsey | 2025-11-02 | 2025-11-03 | 0 | Planned | Design Pending
SP1 | Provider | Registration / KYC | Provider Sign-Up + Docs | Akhsey | 2025-11-03 | 2025-11-04 | 0 | Planned
A4 | Admin / Ops | Dashboard Reports | Graphs + Data for Admin | Akhsey | 2025-11-04 | 2025-11-05 | 50 | Partial | Firestore Linkage
COST1 | Costing | Dynamic Pricing | Variable Pricing Per City | Akhsey | 2025-11-05 | 2025-11-06 | 0 | Planned
R2 | Reports & Analytics | Provider Ratings | Ratings Summary Per Provider | Akhsey | 2025-11-06 | 2025-11-07 | 0 | Planned

## Milestones
Milestone | Description | Target Date | Status | Dependencies
MVP Alpha Launch | OTP + Waitlist Live | 2025-10-30 | Done | Firebase Auth
Feedback Flow | Rating + Thank You Page | 2025-10-31 | Done | Feedback DB
reCAPTCHA Invisible | Hide Visible Widget | 2025-10-31 | In Progress | LaunchingSoonWidget
GitHub + Vercel Sync | Connect Repos & CI | 2025-10-31 | In Progress | GitHub

## Change Log
Date,Change,Description,By,Status
2025-10-30,Firebase Hosting,Production Deployed,Akhsey,Done
2025-10-31,Feedback UI,Thank-You Animation Added,Akhsey,Done
2025-10-31,OTP Widget,Production Success,Akhsey,Done
2025-11-01,Tracker Setup,Master Tracker Created,Akhsey,Planned

## Next SprintPriority,Task,Owner,
Priority,Task,Owner,Planned Date,Status
High,reCAPTCHA Invisible Fix,Akhsey,2025-11-01,Planned
High,GitHub & Vercel Sync,Akhsey,2025-11-01,Planned
Medium,Booking Flow UI,Akhsey,2025-11-02,Planned
Medium,Provider Registration,Akhsey,2025-11-03,Planned
Medium,Costing Model Integration,Akhsey,2025-11-04,Planned

## Auto Summary
Metric,Value
Total Tasks,=SUM('Dashboard Summary'!B2:B7)
Completed,=SUM('Dashboard Summary'!C2:C7)
Overall %,=IF(B1=0,0,ROUND(B2/B1*100,0))
Active Modules,=COUNTA('Dashboard Summary'!A2:A7)
Next Milestone,=INDEX('Dashboard Summary'!G2:G7,MATCH(MIN('Dashboard Summary'!C2:C7),'Dashboard Summary'!C2:C7,0))
Total Bugs | 3
Open Bugs | 1
Resolved Bugs | 2
Overdue Bugs | 6

## Bug_Issue Tracker
ID | Module | Reported By | Date Reported | Severity | Issue Title | Description | Status | Owner | Target Fix Date | Date Resolved | Resolution Notes | Days Open | Overdue
B001 | Customer | Akhsey | 2025-10-31 | High | OTP Verification Loop | OTP not verifying properly in dev environment | Resolved | Dev Team | 2025-10-31 | 2025-10-31 | ReCaptcha reinit fixed | =IF(K2="" | TODAY()-D2 | K2-D2) | =IF(AND(K2="" | J2<TODAY()) | ⚠️ Yes | No)
B002 | Feedback | Akhsey | 2025-10-31 | Medium | Feedback Form Alignment | Fields not aligned after animation update | Resolved | UI Team | 2025-10-31 | 2025-10-31 | CSS grid adjusted | =IF(K3="" | TODAY()-D3 | K3-D3) | =IF(AND(K3="" | J3<TODAY()) | ⚠️ Yes | No)
B003 | Admin | Akhsey | 2025-11-01 | Low | Report Table Pagination | Admin table shows only 10 rows | Open | Dev Team | 2025-11-02 |  | Pending pagination logic | =IF(K4="" | TODAY()-D4 | K4-D4) | =IF(AND(K4="" | J4<TODAY()) | ⚠️ Yes | No)
B004 | Provider | Akhsey | 2025-11-01 | High | Provider Registration Crash | Error on submit after KYC upload | In Progress | Backend | 2025-11-02 |  | Investigating storage limits | =IF(K5="" | TODAY()-D5 | K5-D5) | =IF(AND(K5="" | J5<TODAY()) | ⚠️ Yes | No)

## Bug_Issue_Tracker
ID | Module | Reported By | Date Reported | Severity | Issue Title | Description | Status | Owner | Target Fix Date | Date Resolved | Resolution Notes | Days Open | Overdue
B001 | Customer | Akhsey | 2025-10-31 | High | OTP Verification Loop | OTP not verifying properly in dev environment | Resolved | Dev Team | 2025-10-31 | 2025-10-31 | ReCaptcha reinit fixed | 0 | No
B002 | Feedback | Akhsey | 2025-10-31 | Medium | Feedback Form Alignment | Fields misaligned after animation update | Resolved | UI Team | 2025-10-31 | 2025-10-31 | CSS grid adjusted | 0 | No
B003 | Admin | Akhsey | 2025-11-01 | Low | Report Table Pagination | Admin table shows only 10 rows | Open | Dev Team | 2025-11-02 |  | Pending pagination logic | -1 | No
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
Formulas:
Days Open = IF([Date Resolved]="",TODAY()-[Date Reported],[Date Resolved]-[Date Reported])
Overdue = IF(AND([Date Resolved]="",[Target Fix Date]<TODAY()),"⚠️ Yes","No")