## Dashboard Summary
Module | Total Tasks | Completed | Pending | % Complete | Status | Next Milestone
Customer | 10 | 4 | 6 | Customer | 2.6667 | 0.66667 | 0)) | In Progress | Booking Flow UI (Nov 2)
Service Provider | 8 | 3 | 5 | Service Provider | 2.3333 | 0.83333 | 0)) | In Progress | Registration (Nov 3)
Admin / Ops | 9 | 5 | 4 | Admin / Ops | 1 | -1.5 | 0)) | Good | Reports UI (Nov 2)
Costing | 6 | 1 | 5 | Costing | 3 | 2.5 | 0)) | Low Progress | Pricing Logic (Nov 4)
Reports & Analytics | 6 | 1 | 5 | Reports & Analytics | 3 | 2.5 | 0)) | Low Progress | Analytics (Nov 5)
Backend / Infra | 8 | 5 | 3 | Backend / Infra | 0.33333 | -2.1667 | 0)) | Stable | Vercel Integration (Nov 1)
TOTAL | 47 | 19 | 28 | TOTAL | 12.3333 | 2.8333 | 0))
Bug_Issue_Tracker | 99 | 2 | 1 | Bug_Issue_Tracker | 3 | 0

## Detailed Tracker
ID | Module | Task | Description | Owner | Start Date | Target Date | % Complete | Status | Notes
C1 | Customer | Home Page | Service Discovery UI | Akhsey | 2025-10-28 | 2025-10-29 | 100 | Done | Verified
C3 | Customer | Booking Flow | Select + Schedule Service | Akhsey | 2025-11-02 | 2025-11-03 | 0 | Planned | Design Pending
SP1 | Provider | Registration / KYC | Provider Sign-Up + Docs | Akhsey | 2025-11-03 | 2025-11-04 | 0 | Planned
A4 | Admin / Ops | Dashboard Reports | Graphs + Data for Admin | Akhsey | 2025-11-04 | 2025-11-05 | 50 | Partial | Firestore Linkage
COST1 | Costing | Dynamic Pricing | Variable Pricing Per City | Akhsey | 2025-11-05 | 2025-11-06 | 0 | Planned
R2 | Reports & Analytics | Provider Ratings | Ratings Summary Per Provider | Akhsey | 2025-11-06 | 2025-11-07 | 0 | Planned

## Milestones
Milestone | Description | Target Date | Status | Dependencies
MVP Alpha Launch | OTP + Waitlist Live | 2025-10-30 | Done | Firebase Auth
Feedback Flow | Rating + Thank You Page | 2025-10-31 | Done | Feedback DB
reCAPTCHA Invisible | Hide Visible Widget | 2025-10-31 | In Progress | LaunchingSoonWidget
GitHub + Vercel Sync | Connect Repos & CI | 2025-10-31 | In Progress | GitHub

## Change Log
Date | Change | Description | By | Status
2025-10-30 | Firebase Hosting | Production Deployed | Akhsey | Done
2025-10-31 | Feedback UI | Thank-You Animation Added | Akhsey | Done
2025-10-31 | OTP Widget | Production Success | Akhsey | Done
2025-11-01 | Tracker Setup | Master Tracker Created | Akhsey | Planned

## Next SprintPriority,Task,Owner,
Priority | Task | Owner | Planned Date | Status
High | reCAPTCHA Invisible Fix | Akhsey | 2025-11-01 | Planned
High | GitHub & Vercel Sync | Akhsey | 2025-11-01 | Planned
Medium | Booking Flow UI | Akhsey | 2025-11-02 | Planned
Medium | Provider Registration | Akhsey | 2025-11-03 | Planned
Medium | Costing Model Integration | Akhsey | 2025-11-04 | Planned

## Auto Summary
Metric,Value
Total Tasks,=SUM('Dashboard Summary'!B2:B7)
Completed,=SUM('Dashboard Summary'!C2:C7)
Overall %,=IF(B1=0,0,ROUND(B2/B1*100,0))
Active Modules,=COUNTA('Dashboard Summary'!A2:A7)
Next Milestone,=INDEX('Dashboard Summary'!G2:G7,MATCH(MIN('Dashboard Summary'!C2:C7),'Dashboard Summary'!C2:C7,0))
Total Bugs | 99
Open Bugs | 1
Resolved Bugs | 2
Overdue Bugs | 46

## Bug_Issue Tracker
ID,Module,Reported By,Date Reported,Severity,Issue Title,Description,Status,Owner,Target Fix Date,Date Resolved,Resolution Notes,Days Open,Overdue
B001,Customer,Akhsey,2025-10-31,High,OTP Verification Loop,"OTP not verifying properly in dev environment","Resolved",Dev Team,2025-10-31,2025-10-31,"ReCaptcha reinit fixed",=IF(K2="",TODAY()-D2,K2-D2),=IF(AND(K2="",J2<TODAY()),"⚠️ Yes","No")
B002,Feedback,Akhsey,2025-10-31,Medium,Feedback Form Alignment,"Fields not aligned after animation update","Resolved",UI Team,2025-10-31,2025-10-31,"CSS grid adjusted",=IF(K3="",TODAY()-D3,K3-D3),=IF(AND(K3="",J3<TODAY()),"⚠️ Yes","No")
B003,Admin,Akhsey,2025-11-01,Low,Report Table Pagination,"Admin table shows only 10 rows","Open",Dev Team,2025-11-02,,"Pending pagination logic",=IF(K4="",TODAY()-D4,K4-D4),=IF(AND(K4="",J4<TODAY()),"⚠️ Yes","No")
B004,Provider,Akhsey,2025-11-01,High,Provider Registration Crash,"Error on submit after KYC upload","In Progress",Backend,2025-11-02,,"Investigating storage limits",=IF(K5="",TODAY()-D5,K5-D5),=IF(AND(K5="",J5<TODAY()),"⚠️ Yes","No")

## Bug_Issue_Tracker
ID | Module | Reported By | Date Reported | Severity | Issue Title | Description | Status | Owner | Target Fix Date | Date Resolved | Resolution Notes | Days Open | Overdue
B001 | Customer | Akhsey | 2025-10-31 | High | OTP Verification Loop | OTP not verifying properly in dev environment | Resolved | Dev Team | 2025-10-31 | 2025-10-31 | ReCaptcha reinit fixed | 0 | No
B002 | Feedback | Akhsey | 2025-10-31 | Medium | Feedback Form Alignment | Fields misaligned after animation update | Resolved | UI Team | 2025-10-31 | 2025-10-31 | CSS grid adjusted | 0 | No
B003 | Admin | Akhsey | 2025-11-01 | Low | Report Table Pagination | Admin table shows only 10 rows | Open | Dev Team | 2025-11-02 |  | Pending pagination logic | -1 | No
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
[12 empty] | 45961 | ⚠️ Yes
Formulas:
Days Open = IF([Date Resolved]="",TODAY()-[Date Reported],[Date Resolved]-[Date Reported])
Overdue = IF(AND([Date Resolved]="",[Target Fix Date]<TODAY()),"⚠️ Yes","No")