## SevaSetu_Master_TaskList_v1.4.x
Module | Task ID | Task Name | Status | ETA | Priority | Owner / Assigned To | Notes
=== CUSTOMER MODULE ===
Customer | C1 | Booking Flow UI + UX Finalization | In Progress | 2025-11-02 | High
Customer | C2 | Add Thank You Page (âœ… animation) | Done | - | Low
Customer | C3 | Feedback Widget Integration (show + submit) | Done | - | Low
Customer | C4 | Feedback Database Connection (Firestore) | Done | - | Low
Customer | C5 | Booking Confirmation Redirect to Feedback | Pending | 2025-11-02 | High
Customer | C6 | OTP Verification for Booking Users | Done | - | High
Customer | C7 | Mobile Responsive Layout Fixes | In Progress | 2025-11-03 | Medium
Customer | C8 | Customer Dashboard Summary (My Bookings) | Planned | 2025-11-05 | Medium
Customer | C9 | Service Rating + Edit Feedback | Planned | 2025-11-06 | Medium
Customer | C10 | Push Notification Integration | Future | 2025-11-10 | Low
=== SERVICE PROVIDER MODULE ===
Service Provider | S1 | Provider Registration Form + OTP | In Progress | 2025-11-03 | High
Service Provider | S2 | Provider Dashboard (Earnings + Bookings) | Planned | 2025-11-04 | Medium
Service Provider | S3 | Service Category Selection UI | Done | - | Low
Service Provider | S4 | Availability Toggle (Online/Offline) | Planned | 2025-11-05 | Medium
Service Provider | S5 | Add/View Feedback by Customers | Pending | 2025-11-05 | Medium
Service Provider | S6 | Provider Profile Edit & Upload (Photo | Docs) | Planned | 2025-11-06 | Medium
Service Provider | S7 | Earnings Summary Graph | Planned | 2025-11-07 | Medium
Service Provider | S8 | Logout + Account Delete Flow | Done | - | Low
=== ADMIN / OPERATIONS ===
Admin | A1 | Admin Login & Role Guard | Done | - | Low
Admin | A2 | Dashboard Overview (Bookings | Feedback) | Done | - | Low
Admin | A3 | Reports UI â€“ Bookings Summary Table | In Progress | 2025-11-02 | Medium
Admin | A4 | Feedback Review Page | Planned | 2025-11-03 | Medium
Admin | A5 | Bug Tracker Integration (auto import sheet) | Pending | 2025-11-04 | Medium
Admin | A6 | Add User Management Tab | Planned | 2025-11-05 | Medium
Admin | A7 | Analytics Graph (Bookings Trend | Feedback Rating) | Planned | 2025-11-06 | Medium
Admin | A8 | Admin Notification Control (Email/Push) | Future | 2025-11-09 | Low
Admin | A9 | Firestore Role Update APIs | Done | - | Low
=== COSTING & PAYMENTS ===
Payments | P1 | Costing Table Schema (Firestore) | Done | - | Low
Payments | P2 | Admin Service Cost Override | Pending | 2025-11-04 | High
Payments | P3 | Dynamic GST + Platform Fee Calculation | Pending | 2025-11-04 | High
Payments | P4 | Payment Gateway (Stripe/Razorpay) | Future | 2025-11-07 | Medium
Payments | P5 | Auto Email Receipt after Payment | Planned | 2025-11-08 | Medium
Payments | P6 | Refund / Cancellation Logic | Future | 2025-11-10 | Low
=== REPORTS & ANALYTICS ===
Reports | R1 | Feedback Summary Report | Pending | 2025-11-05 | Medium
Reports | R2 | Waitlist User Growth Report | Pending | 2025-11-05 | Medium
Reports | R3 | Booking Revenue Chart (Month-wise) | Planned | 2025-11-06 | Medium
Reports | R4 | Export to CSV/PDF | Planned | 2025-11-06 | Medium
Reports | R5 | Dashboard Graph for Daily Bookings | Planned | 2025-11-06 | Medium
Reports | R6 | Service Category Trend Analysis | Planned | 2025-11-08 | Medium
=== BACKEND / INFRASTRUCTURE ===
Backend | B1 | Firebase Hosting (Production + Dev) | Done | - | Low
Backend | B2 | Firestore Rules + Optimization | Done | - | Low
Backend | B3 | Firebase Auth Domain Whitelist | Done | - | Low
Backend | B4 | Automatic Daily Backup (Cloud Function) | Done | - | Low
Backend | B5 | CI/CD with GitHub Actions + Vercel | Pending | 2025-11-01 | Medium
Backend | B6 | Error Logging via Firebase Functions | Planned | 2025-11-04 | Medium
Backend | B7 | Analytics Event Tracking | Planned | 2025-11-06 | Medium
Backend | B8 | Firebase Region Failover Setup | Future | 2025-11-10 | Low
=== BUG / ISSUE TRACKER ===
Bug | BG1 | Create Tracker Sheet (auto) | Done | - | Low
Bug | BG2 | Add Conditional Color Logic | Pending | 2025-11-01 | Medium
Bug | BG3 | Auto ID Generator (B001...) | Done | - | Low
Bug | BG4 | Link Admin â€œBugsâ€ Tab to Sheet | Planned | 2025-11-03 | Medium
Bug | BG5 | Add Auto â€œLast Updatedâ€ Cell | Pending | 2025-11-01 | Medium
Bug | BG6 | Daily Report Export to PDF | Planned | 2025-11-06 | Medium

## Sheet1
=== DASHBOARD SUMMARY ===
Summary | CS1 | Customer Features | 80% | 100% | Medium
Summary | CS2 | Provider Features | 60% | 100% | In Progress
Summary | CS3 | Admin Features | 70% | 100% | Medium
Summary | CS4 | Costing | 40% | 100% | Low
Summary | CS5 | Backend | 85% | 100% | Stable
Summary | CS6 | Reports/Analytics | 50% | 100% | Medium
Summary | CS7 | Bugs Fixed | 2 | 20 | Medium
Summary | CS8 | Overall Project Progress | 67% | 100% | On Track